## Legend
VRX Master WBS - full TNSR parity + complete VPP 26.06 feature surface
Baseline: VPP 26.06 (released 24 June 2026, 28 new features). TNSR scope from Netgate's published feature documentation. Prepared 2026-09-23.
HOW TO USE THIS WORKBOOK
Assumptions | Every lever lives here: delivery FTE, effective PD per FTE-year, overhead factor, Q1 ramp, project start date. Change these and all other sheets recalculate.
WBS | The 102 work items. Edit ONLY the blue columns: Tier, Net PD, Start Q, End Q, Squad, Status, Owner. Black columns are formulas.
Quarter Plan | Capacity vs planned load per quarter, derived from each item's Start Q..End Q span. Keep utilisation at or below 100%.
Summary | Roll-ups by domain, tier and squad. All SUMIF - no hardcoded totals.
Releases | Release train with gate IDs and measurable acceptance criteria. Net PD per release is derived from the WBS.
Sprints | Sprint-level plan for the first six months. Dates derive from the project start date.
Team | Squads, headcount, hiring month.
CapEx | Lab hardware. Without the month-4 traffic generator no performance number is defensible.
Scenarios | Duration for five scope/team combinations, computed from the tier totals.
COLOUR CONVENTION
Blue text | Hardcoded input - you are expected to edit it.
Black text | Formula - leave it alone.
Green text | Link to another sheet.
Yellow fill | Key assumption.
ESTIMATING BASIS
Unit | Person-day (PD) of a mid-to-senior engineer. Effective working year = 190 PD after holidays, leave, meetings and support duty.
What one PD includes | All nine 'definition of done' conditions: data plane proven by a packet-level test; survives vpp restart and reboot; REST endpoint + OpenAPI + generated client; candidate/commit/rollback with failure paths; UI screen with schema-driven form and live status; en+fa strings; unit/integration/E2E tests; user doc + CLI equivalent; audit entry. Pure coding is about 45% of each number.
Tiers | T1 = needed to sell. T2 = needed for TNSR parity. T3 = complete VPP coverage, low commercial value.
Source of the numbers | Bottom-up expert judgement per domain, calibrated against the published TNSR feature set and the VPP 26.06 plugin inventory. No vendor figures exist for this scope - treat every estimate as an assumption and re-base it after Gate G2 (month 6), when the team's real velocity is measurable.
EXAMPLE ROW (WBS sheet)
D3.4 ¦ D3 ¦ Dynamic Routing ¦ OSPFv2 ¦ T1 ¦ 55 ¦ 5 ¦ 5 ¦ S2 ¦ D3.2 ¦ Not started | ID ¦ Domain ¦ Domain name ¦ Work item ¦ Tier ¦ Net PD ¦ Start Q ¦ End Q ¦ Squad ¦ Depends on ¦ Status

## Assumptions
Assumptions and levers
Blue cells on a yellow fill are inputs. Every other figure in this workbook derives from them.
Lever | Value | Note
Delivery FTE | 14 | Engineers + QA + 50% of the architect. Headcount is 15-16.
Effective PD per FTE per year | 190 | 260 working days minus holidays, leave, meetings and support duty.
Overhead factor on estimates | 1.25 | Management, cross-squad integration and rework. Applied to every net estimate.
Quarters in plan | 12 | 36 months.
Q1 ramp factor | 0.5 | Hiring and onboarding - the first quarter delivers at half capacity.
Project start date | 2026-10-01 | Drives every date on the Sprints sheet.
Sprint length (weeks) | 2 | Used by the Sprints sheet.
Ramp-up + stabilisation months | 5 | Calendar time no amount of staffing removes: ~1.5 months lost to hiring and onboarding, ~3.5 months of release stabilisation and gates. Added to every scenario's delivery months.
DERIVED
Capacity per full quarter (PD) | 665 | Delivery FTE x PD per year / 4
Total plan capacity (PD) | 7647.5 | 11 full quarters + one ramp quarter
Net scope (PD) | 5185 | Sum of every WBS item
Loaded scope (PD) | 6481.25 | Net scope x overhead factor
Utilisation of capacity | 84.75% | Keep below 100% - the remainder is the contingency reserve
Contingency reserve | 15.25% | Do not spend this on new scope before month 30
Delivery months at full capacity | 29.2387 | Excludes ramp-up and release-stabilisation time
Re-base every figure on this sheet after Gate G2 (month 6), when the team's measured velocity replaces judgement.

## WBS
ID | Domain | Domain name | Work item | Tier | Net PD | Loaded PD | Start Q | End Q | Quarters | PD / quarter | Squad | Release | Depends on | Status | Owner | Notes
D0.1 | D0 | Foundation & Platform | Monorepo, CI/CD, codegen pipeline (Zod -> OpenAPI -> client -> proto -> binapi) | T1 | 25 | 31.25 | 1 | 1 | 1 | 25 | S6 | R0.1 Alpha |  | Not started |  | CI must fail on dirty generated output
D0.2 | D0 | Foundation & Platform | Pinned VPP fork, patch management, VPP package build | T1 | 30 | 37.5 | 1 | 2 | 2 | 15 | S6 | R0.1 Alpha | D0.1 | Not started |  | Track a stable release branch, never master
D0.3 | D0 | Foundation & Platform | OS image: Ubuntu 24.04 autoinstall + installer ISO | T1 | 45 | 56.25 | 2 | 3 | 2 | 22.5 | S6 | R0.5 Beta (MVP) | D0.2 | Not started
D0.4 | D0 | Foundation & Platform | Debian packaging, signed APT repository | T1 | 25 | 31.25 | 1 | 2 | 2 | 12.5 | S6 | R0.1 Alpha | D0.1 | Not started
D0.5 | D0 | Foundation & Platform | A/B image upgrade with automatic rollback | T1 | 40 | 50 | 6 | 6 | 1 | 40 | S6 | R1.0 GA-1 | D0.3 | Not started |  | Required for GA-1
D0.6 | D0 | Foundation & Platform | startup.conf generator: hugepages, workers, RSS, NUMA, isolcpus, PCI whitelist | T1 | 30 | 37.5 | 2 | 2 | 1 | 30 | S1 | R0.1 Alpha | D0.2 | Not started
D0.7 | D0 | Foundation & Platform | Agent core: govpp connection, stats reader, reconciler/KVScheduler, dependency graph | T1 | 70 | 87.5 | 1 | 2 | 2 | 35 | S1 | R0.1 Alpha | D0.2 | Not started |  | CRITICAL PATH - everything depends on this
D0.8 | D0 | Foundation & Platform | API core: NestJS, candidate/running datastore, atomic commit, confirmed-commit, revisions, rollback | T1 | 75 | 93.75 | 1 | 2 | 2 | 37.5 | S4 | R0.1 Alpha | D0.1 | Not started |  | CRITICAL PATH
D0.9 | D0 | Foundation & Platform | Auth, RBAC, audit log, API keys, TLS, TPM-backed secret store | T1 | 55 | 68.75 | 2 | 2 | 1 | 55 | S4 | R0.1 Alpha | D0.8 | Not started
D0.10 | D0 | Foundation & Platform | UI shell: theme, layout, i18n en/fa + RTL, SchemaForm renderer, DataGrid wrapper, WS client | T1 | 80 | 100 | 1 | 2 | 2 | 40 | S5 | R0.1 Alpha | D0.8 | Not started
D0.11 | D0 | Foundation & Platform | Interactive CLI (clixon-like: config mode, completion, show commands) | T1 | 90 | 112.5 | 6 | 7 | 2 | 45 | S4 | R1.5 GA-2 | D0.8 | Not started |  | TNSR's primary interface
D0.12 | D0 | Foundation & Platform | Telemetry pipeline: stats -> gRPC stream -> WS fan-out -> Prometheus -> history | T1 | 50 | 62.5 | 2 | 3 | 2 | 25 | S4 | R0.5 Beta (MVP) | D0.7 | Not started
D0.13 | D0 | Foundation & Platform | Test infra: containerlab/QEMU lab, Robot Framework, TRex harness, Playwright | T1 | 70 | 87.5 | 1 | 2 | 2 | 35 | QA | R0.1 Alpha | D0.1 | Not started
D1.1 | D1 | Interfaces & L2 | NIC inventory and driver binding: dpdk, rdma, af_xdp, af_packet, vmxnet3, virtio, vhost-user, tap-v2, netmap, memif, pipe, Marvell mGig | T1 | 70 | 87.5 | 2 | 3 | 2 | 35 | S1 | R0.5 Beta (MVP) | D0.6 | Not started |  | Fix a supported-hardware matrix; refuse 'any NIC'
D1.2 | D1 | Interfaces & L2 | Interface basics: admin state, MTU, MAC, promisc, rx-mode, rx/tx queues, worker placement | T1 | 35 | 43.75 | 2 | 2 | 1 | 35 | S1 | R0.1 Alpha | D0.7 | Not started
D1.3 | D1 | Interfaces & L2 | IPv4/IPv6 addressing + IP unnumbered | T1 | 20 | 25 | 2 | 2 | 1 | 20 | S1 | R0.1 Alpha | D1.2 | Not started
D1.4 | D1 | Interfaces & L2 | 802.1q sub-interfaces + QinQ/802.1ad stacking | T1 | 25 | 31.25 | 2 | 2 | 1 | 25 | S1 | R0.1 Alpha | D1.2 | Not started
D1.5 | D1 | Interfaces & L2 | Bonding: LACP, XOR, round-robin, active-backup | T1 | 30 | 37.5 | 2 | 3 | 2 | 15 | S1 | R0.5 Beta (MVP) | D1.2 | Not started
D1.6 | D1 | Interfaces & L2 | L2: bridge domains, cross-connect, L2XC, L3XC, split-horizon, MAC aging, time-range MAC filter | T1 | 45 | 56.25 | 2 | 3 | 2 | 22.5 | S1 | R0.5 Beta (MVP) | D1.2 | Not started
D1.7 | D1 | Interfaces & L2 | LLDP | T2 | 12 | 15 | 3 | 3 | 1 | 12 | S1 | R0.5 Beta (MVP) | D1.2 | Not started
D1.8 | D1 | Interfaces & L2 | VNET GSO, checksum offload, jumbo frames | T1 | 20 | 25 | 4 | 4 | 1 | 20 | S1 | R0.5 Beta (MVP) | D1.2 | Not started
D1.9 | D1 | Interfaces & L2 | Network Delay Simulator (nsim) | T3 | 8 | 10 | 10 | 10 | 1 | 8 | S1 | R2.0 GA-3 | D1.2 | Not started |  | Test tool, not a product feature
D1.10 | D1 | Interfaces & L2 | SPAN / ERSPAN mirroring | T2 | 25 | 31.25 | 7 | 7 | 1 | 25 | S1 | R1.5 GA-2 | D1.6 | Not started
D1.11 | D1 | Interfaces & L2 | Loopback / BVI interfaces | T1 | 10 | 12.5 | 3 | 3 | 1 | 10 | S1 | R0.5 Beta (MVP) | D1.6 | Not started
D2.1 | D2 | L3, MPLS & Multicast | VRF/table management + Source VRF Select | T1 | 30 | 37.5 | 3 | 3 | 1 | 30 | S2 | R0.5 Beta (MVP) | D1.3 | Not started
D2.2 | D2 | L3, MPLS & Multicast | Static routes v4/v6, ECMP, weighted paths, DPO/adjacency view | T1 | 35 | 43.75 | 3 | 3 | 1 | 35 | S2 | R0.5 Beta (MVP) | D2.1 | Not started
D2.3 | D2 | L3, MPLS & Multicast | Neighbour DB: ARP, ND, proxy-ND, IPv6 RA, IPv6 DAD (new in 26.06) | T1 | 30 | 37.5 | 3 | 3 | 1 | 30 | S1 | R0.5 Beta (MVP) | D1.3 | Not started
D2.4 | D2 | L3, MPLS & Multicast | RPF strict/loose, ADL allow/deny lists, Auto-SDL | T2 | 30 | 37.5 | 9 | 9 | 1 | 30 | S2 | R2.0 GA-3 | D2.2 | Not started
D2.5 | D2 | L3, MPLS & Multicast | FIB browser with server-side pagination (1M+ routes) | T1 | 25 | 31.25 | 3 | 4 | 2 | 12.5 | S5 | R0.5 Beta (MVP) | D2.2 | Not started
D2.6 | D2 | L3, MPLS & Multicast | Tools: ping, traceroute, ARP flush | T1 | 20 | 25 | 3 | 3 | 1 | 20 | S4 | R0.5 Beta (MVP) | D2.2 | Not started
D2.7 | D2 | L3, MPLS & Multicast | Classifier/classify tables, IP session redirect, ACL-Based Forwarding (PBR) | T2 | 45 | 56.25 | 5 | 5 | 1 | 45 | S2 | R1.0 GA-1 | D2.2 | Not started
D2.8 | D2 | L3, MPLS & Multicast | MPLS: label operations, LSP, MPLS-over-Ethernet, basic L3VPN, SR-MPLS | T2 | 90 | 112.5 | 9 | 10 | 2 | 45 | S2 | R2.0 GA-3 | D3.3 | Not started
D2.9 | D2 | L3, MPLS & Multicast | Multicast: IGMPv3, PIM via FRR, mfib, BIER | T3 | 70 | 87.5 | 9 | 10 | 2 | 35 | S2 | R2.0 GA-3 | D3.2 | Not started |  | BIER has near-zero commercial demand
D3.1 | D3 | Dynamic Routing | linux-cp / linux-nl hardening: interface pairs, state/MTU sync, VRF mapping, IPv6, full-table performance | T1 | 90 | 112.5 | 3 | 4 | 2 | 45 | S2 | R0.5 Beta (MVP) | D1.2 | Not started |  | CRITICAL PATH - prototype in Q3, not Q5
D3.2 | D3 | Dynamic Routing | FRR lifecycle: renderer framework, JSON state readers, safe reload, dry-run | T1 | 60 | 75 | 4 | 4 | 1 | 60 | S2 | R0.5 Beta (MVP) | D3.1 | Not started
D3.3 | D3 | Dynamic Routing | BGP: core, AFI/SAFI v4/v6, communities, route-maps, prefix-lists, AS-path filters, peer-groups, RR, confederation, graceful restart, BGP Roles (RFC 9234), add-path, VPNv4/VPNv6 | T1 | 140 | 175 | 4 | 5 | 2 | 70 | S2 | R1.0 GA-1 | D3.2 | Not started
D3.4 | D3 | Dynamic Routing | OSPFv2 | T1 | 55 | 68.75 | 5 | 5 | 1 | 55 | S2 | R1.0 GA-1 | D3.2 | Not started
D3.5 | D3 | Dynamic Routing | OSPFv3 | T2 | 40 | 50 | 8 | 8 | 1 | 40 | S2 | R1.5 GA-2 | D3.2 | Not started
D3.6 | D3 | Dynamic Routing | IS-IS | T2 | 45 | 56.25 | 7 | 7 | 1 | 45 | S2 | R1.5 GA-2 | D3.2 | Not started
D3.7 | D3 | Dynamic Routing | RIPv2 / RIPng | T2 | 25 | 31.25 | 8 | 8 | 1 | 25 | S2 | R1.5 GA-2 | D3.2 | Not started
D3.8 | D3 | Dynamic Routing | BFD (native VPP plugin + FRR integration) | T1 | 35 | 43.75 | 5 | 5 | 1 | 35 | S2 | R1.0 GA-1 | D3.2 | Not started
D3.9 | D3 | Dynamic Routing | Policy-based routing in API/UI | T2 | 20 | 25 | 6 | 6 | 1 | 20 | S2 | R1.0 GA-1 | D2.7 | Not started
D3.10 | D3 | Dynamic Routing | Redistribution matrix and route-policy UX | T1 | 30 | 37.5 | 5 | 6 | 2 | 15 | S2 | R1.0 GA-1 | D3.3 | Not started
D4.1 | D4 | NAT & CGNAT | NAT44-ED: sessions, pools, twice-NAT, port-forward, 1:1, interface NAT, hairpinning, session helpers/ALGs | T1 | 90 | 112.5 | 3 | 4 | 2 | 45 | S3 | R0.5 Beta (MVP) | D2.2 | Not started
D4.2 | D4 | NAT & CGNAT | NAT44-EI | T2 | 25 | 31.25 | 7 | 7 | 1 | 25 | S3 | R1.5 GA-2 | D4.1 | Not started
D4.3 | D4 | NAT & CGNAT | NAT64, NAT66, NPTv6 | T2 | 50 | 62.5 | 8 | 8 | 1 | 50 | S3 | R1.5 GA-2 | D4.1 | Not started
D4.4 | D4 | NAT & CGNAT | DET44 deterministic CGNAT + CGNAT logging/IPFIX | T2 | 45 | 56.25 | 7 | 7 | 1 | 45 | S3 | R1.5 GA-2 | D4.1 | Not started
D4.5 | D4 | NAT & CGNAT | DS-Lite, MAP-E, MAP-T, LW4o6 BR, 464XLAT | T2 | 75 | 93.75 | 7 | 8 | 2 | 37.5 | S3 | R1.5 GA-2 | D4.3 | Not started
D4.6 | D4 | NAT & CGNAT | CNAT: policy 1:1, SNAT/DNAT policy (new in 26.06), load-balanced translation | T2 | 45 | 56.25 | 8 | 8 | 1 | 45 | S3 | R1.5 GA-2 | D4.1 | Not started
D4.7 | D4 | NAT & CGNAT | Session browser at 1M+ scale with server-side filter and kill-session | T1 | 35 | 43.75 | 4 | 4 | 1 | 35 | S3 | R0.5 Beta (MVP) | D4.1 | Not started
D5.1 | D5 | Firewall & ACL | Object model: addresses, groups, FQDN, services, schedules, zones, tags | T1 | 50 | 62.5 | 4 | 5 | 2 | 25 | S4 | R1.0 GA-1 | D0.8 | Not started
D5.2 | D5 | Firewall & ACL | ACL plugin: L2 MACIP, L3/L4 stateless and stateful, per-interface in/out, hit counters | T1 | 70 | 87.5 | 5 | 5 | 1 | 70 | S3 | R1.0 GA-1 | D5.1 | Not started
D5.3 | D5 | Firewall & ACL | Host/local-in ACL for management-plane protection + nftables host firewall | T1 | 30 | 37.5 | 6 | 6 | 1 | 30 | S3 | R1.0 GA-1 | D5.2 | Not started
D5.4 | D5 | Firewall & ACL | Rule editor UI for 100,000 rules (virtualised, CSV bulk, reorder, search) | T1 | 60 | 75 | 6 | 6 | 1 | 60 | S5 | R1.0 GA-1 | D5.2 | Not started
D5.5 | D5 | Firewall & ACL | ADL / Auto-SDL integration | T3 | 15 | 18.75 | 10 | 10 | 1 | 15 | S3 | R2.0 GA-3 | D5.2 | Not started |  | Largely covered by ACLs
D5.6 | D5 | Firewall & ACL | Stateful policy state synchronisation for HA (TNSR VPF state sync equivalent) | T2 | 45 | 56.25 | 8 | 8 | 1 | 45 | S3 | R1.5 GA-2 | D9.2 | Not started
D6.1 | D6 | VPN & Tunnels | IPsec core: SA/SPD, tunnel and transport mode, ESP/AH, async crypto, native/ipsecmb/openssl engines, QAT offload | T1 | 80 | 100 | 3 | 3 | 1 | 80 | S3 | R0.5 Beta (MVP) | D1.3 | Not started
D6.2 | D6 | VPN & Tunnels | strongSwan + kernel-vpp/socket-vpp, swanctl.conf renderer, IKEv1/IKEv2, full cipher and DH 1-24/31 matrix, NAT-T, DPD, MOBIKE | T1 | 100 | 125 | 3 | 4 | 2 | 50 | S3 | R0.5 Beta (MVP) | D6.1 | Not started
D6.3 | D6 | VPN & Tunnels | Native VPP IKEv2 plugin path + 26.06 crypto enhancements | T2 | 40 | 50 | 10 | 10 | 1 | 40 | S3 | R2.0 GA-3 | D6.1 | Not started |  | Alternative to strongSwan for responder-only cases
D6.4 | D6 | VPN & Tunnels | PKI: CA, CSR, import/export, CRL/OCSP, ACME, expiry alerts, PKCS#11/HSM | T1 | 60 | 75 | 7 | 7 | 1 | 60 | S3 | R1.5 GA-2 | D6.2 | Not started
D6.5 | D6 | VPN & Tunnels | WireGuard | T1 | 35 | 43.75 | 7 | 7 | 1 | 35 | S3 | R1.5 GA-2 | D6.1 | Not started
D6.6 | D6 | VPN & Tunnels | Tunnels: GRE (L2/L3), IPIP, VXLAN, VXLAN-GPE, GTP-U, L2TPv3, PPPoE, Tunnel Infra, Packet Vector Tunnel | T1 | 90 | 112.5 | 4 | 7 | 4 | 22.5 | S3 | R1.5 GA-2 | D2.2 | Not started |  | GTP-U/L2TPv3/PPPoE are T3-value; schedule last
D6.7 | D6 | VPN & Tunnels | SRv6: core, network programming, service chaining proxies, SRv6-mobile GTP functions | T3 | 110 | 137.5 | 9 | 10 | 2 | 55 | S3 | R2.0 GA-3 | D2.8 | Not started |  | Only large mobile operators need this
D6.8 | D6 | VPN & Tunnels | LISP and LISP-GPE | T3 | 40 | 50 | 10 | 10 | 1 | 40 | S3 | R2.0 GA-3 | D2.2 | Not started |  | Effectively dead technology
D6.9 | D6 | VPN & Tunnels | Remote-access VPN: IKEv2 + EAP + client pools (optional OpenVPN/SSL-VPN) | T2 | 60 | 75 | 9 | 9 | 1 | 60 | S3 | R2.0 GA-3 | D6.4 | Not started
D6.10 | D6 | VPN & Tunnels | Tunnel dashboards, SA/SPI inspection, rekey history, per-tunnel telemetry | T1 | 35 | 43.75 | 6 | 6 | 1 | 35 | S5 | R1.0 GA-1 | D6.2 | Not started
D7.1 | D7 | Services, QoS & Host Stack | Kea DHCPv4/v6 server, reservations, option sets, lease DB and UI | T1 | 60 | 75 | 4 | 5 | 2 | 30 | S4 | R1.0 GA-1 | D1.3 | Not started
D7.2 | D7 | Services, QoS & Host Stack | DHCP relay/proxy (VPP plugin) + DHCP client | T1 | 30 | 37.5 | 4 | 5 | 2 | 15 | S4 | R1.0 GA-1 | D7.1 | Not started
D7.3 | D7 | Services, QoS & Host Stack | DNS: Unbound resolver/forwarder/DNSSEC/views + VPP caching DNS plugin | T1 | 50 | 62.5 | 4 | 5 | 2 | 25 | S4 | R1.0 GA-1 | D1.3 | Not started
D7.4 | D7 | Services, QoS & Host Stack | NTP via chrony (client/server), optional PTP | T1 | 25 | 31.25 | 5 | 5 | 1 | 25 | S4 | R1.0 GA-1 | D0.9 | Not started
D7.5 | D7 | Services, QoS & Host Stack | SNMP v2c/v3 via net-snmp + private MIB | T2 | 45 | 56.25 | 6 | 6 | 1 | 45 | S4 | R1.0 GA-1 | D0.12 | Not started
D7.6 | D7 | Services, QoS & Host Stack | IPFIX/NetFlow (flowprobe) + sFlow | T2 | 50 | 62.5 | 8 | 8 | 1 | 50 | S1 | R1.5 GA-2 | D0.12 | Not started
D7.7 | D7 | Services, QoS & Host Stack | Syslog export + log explorer | T1 | 35 | 43.75 | 9 | 9 | 1 | 35 | S4 | R2.0 GA-3 | D0.12 | Not started
D7.8 | D7 | Services, QoS & Host Stack | QoS: policer, shaper, QoS record/map/mark, DSCP/dot1p, hierarchical HQoS, per-interface queues | T2 | 85 | 106.25 | 7 | 8 | 2 | 42.5 | S1 | R1.5 GA-2 | D1.2 | Not started
D7.9 | D7 | Services, QoS & Host Stack | Load Balancer plugin (GRE/NAT/L3DSR/maglev) | T3 | 40 | 50 | 10 | 10 | 1 | 40 | S1 | R2.0 GA-3 | D4.1 | Not started |  | Solved outside the product by HAProxy/nginx
D7.10 | D7 | Services, QoS & Host Stack | Host Stack: session layer, TCP/UDP tuning, VCL, TLS engines, QUIC/quicly, HTTP static server, HTTP/3 CONNECT + UDP proxying, SRTP, HSI | T3 | 130 | 162.5 | 10 | 11 | 2 | 65 | S1 | R2.5 GA-Final | D0.7 | Not started |  | No router customer asks for this
D7.11 | D7 | Services, QoS & Host Stack | Packet generator (PG) + pcap tooling in UI | T2 | 25 | 31.25 | 7 | 7 | 1 | 25 | S1 | R1.5 GA-2 | D8.2 | Not started
D8.1 | D8 | Observability & Ops | Dashboard, charts, per-worker CPU, queue/buffer stats, buffers monitoring, buffer metadata tracker | T1 | 60 | 75 | 3 | 6 | 4 | 15 | S5 | R1.0 GA-1 | D0.12 | Not started
D8.2 | D8 | Observability & Ops | Packet capture: pcap rx/tx/drop, BPF Trace Filter, trace node, Trace Path plugin (new 26.06), G2 export | T1 | 55 | 68.75 | 7 | 8 | 2 | 27.5 | S1 | R1.5 GA-2 | D0.7 | Not started
D8.3 | D8 | Observability & Ops | Prometheus exporter (VPP prom plugin + own metrics) + Grafana dashboards | T1 | 35 | 43.75 | 6 | 6 | 1 | 35 | S4 | R1.0 GA-1 | D0.12 | Not started
D8.4 | D8 | Observability & Ops | Event and alarm engine, thresholds, email/webhook/SNMP traps | T1 | 45 | 56.25 | 4 | 5 | 2 | 22.5 | S4 | R1.0 GA-1 | D0.12 | Not started
D8.5 | D8 | Observability & Ops | Backup/restore, scheduled export, config templates, bulk provisioning | T1 | 40 | 50 | 5 | 5 | 1 | 40 | S4 | R1.0 GA-1 | D0.8 | Not started
D8.6 | D8 | Observability & Ops | Support bundle / sysdump | T1 | 20 | 25 | 9 | 9 | 1 | 20 | S6 | R2.0 GA-3 | D0.12 | Not started
D8.7 | D8 | Observability & Ops | Upgrade UI and staged rollout | T1 | 25 | 31.25 | 6 | 6 | 1 | 25 | S5 | R1.0 GA-1 | D0.5 | Not started
D8.8 | D8 | Observability & Ops | RESTCONF/NETCONF compatibility layer + YANG models | T2 | 90 | 112.5 | 7 | 8 | 2 | 45 | S4 | R1.5 GA-2 | D0.8 | Not started |  | Needed for TNSR API parity
D8.9 | D8 | Observability & Ops | Terraform provider, Ansible collection, Python SDK | T2 | 55 | 68.75 | 10 | 10 | 1 | 55 | S4 | R2.0 GA-3 | D0.8 | Not started
D9.1 | D9 | High Availability | VRRPv3 (native VPP plugin) + keepalived path | T1 | 45 | 56.25 | 6 | 6 | 1 | 45 | S1 | R1.0 GA-1 | D1.3 | Not started
D9.2 | D9 | High Availability | Config synchronisation between peers, cluster membership | T1 | 50 | 62.5 | 6 | 7 | 2 | 25 | S4 | R1.5 GA-2 | D0.8 | Not started
D9.3 | D9 | High Availability | State sync: NAT/ACL sessions and IPsec SAs | T2 | 60 | 75 | 8 | 8 | 1 | 60 | S3 | R1.5 GA-2 | D9.2 | Not started
D9.4 | D9 | High Availability | Failover test automation and convergence tuning | T1 | 30 | 37.5 | 8 | 8 | 1 | 30 | QA | R1.5 GA-2 | D9.3 | Not started
D9.5 | D9 | High Availability | Cluster view in UI | T2 | 25 | 31.25 | 8 | 8 | 1 | 25 | S5 | R1.5 GA-2 | D9.2 | Not started
D10.1 | D10 | Multi-tenancy & AAA | VDOM/tenant model, per-tenant RBAC and API scoping | T2 | 70 | 87.5 | 10 | 11 | 2 | 35 | S4 | R2.5 GA-Final | D0.9 | Not started |  | Changes the data model - decide in Q1 whether it is in scope
D10.2 | D10 | Multi-tenancy & AAA | AAA: RADIUS, TACACS+, LDAP, SAML, OIDC + MFA | T2 | 55 | 68.75 | 9 | 9 | 1 | 55 | S4 | R2.0 GA-3 | D0.9 | Not started
D11.1 | D11 | Cloud & Virtualization | Cloud images AWS/Azure/GCP + marketplace, cloud-init, ENA/Hyper-V drivers, cloud routing integration | T2 | 90 | 112.5 | 10 | 11 | 2 | 45 | S6 | R2.5 GA-Final | D0.3 | Not started
D11.2 | D11 | Cloud & Virtualization | KVM/VMware/Hyper-V/Proxmox images + SR-IOV and PCI passthrough | T1 | 40 | 50 | 9 | 9 | 1 | 40 | S6 | R2.0 GA-3 | D0.3 | Not started
D12.1 | D12 | Hardening, QA, Docs & Release | CIS hardening, secure boot, package signing, offline (air-gapped) update bundle | T1 | 60 | 75 | 11 | 11 | 1 | 60 | S6 | R2.5 GA-Final | D0.4 | Not started
D12.2 | D12 | Hardening, QA, Docs & Release | Licensing and entitlement enforcement | T1 | 40 | 50 | 11 | 11 | 1 | 40 | S4 | R2.5 GA-Final | D0.9 | Not started
D12.3 | D12 | Hardening, QA, Docs & Release | Independent penetration test + remediation | T1 | 45 | 56.25 | 12 | 12 | 1 | 45 | QA | R2.5 GA-Final | D12.1 | Not started
D12.4 | D12 | Hardening, QA, Docs & Release | Full user documentation (~400 pages) + CLI reference + API reference | T1 | 120 | 150 | 9 | 12 | 4 | 30 | Writer | R2.5 GA-Final |  | Not started |  | Technical writer from M12
D12.5 | D12 | Hardening, QA, Docs & Release | QA: regression suite growth, nightly topology, perf CI, interop matrix (Cisco/Juniper/FortiGate/strongSwan/AWS VGW) | T1 | 160 | 200 | 4 | 12 | 9 | 17.7778 | QA | R2.5 GA-Final | D0.13 | Not started |  | Continuous from Q4 to GA
D12.6 | D12 | Hardening, QA, Docs & Release | Soak and chaos: kill -9, link flap, 72h at line rate | T1 | 50 | 62.5 | 11 | 12 | 2 | 25 | QA | R2.5 GA-Final | D12.5 | Not started
D12.7 | D12 | Hardening, QA, Docs & Release | Certification preparation (Common Criteria / local standards) | T2 | 60 | 75 | 11 | 12 | 2 | 30 | S6 | R2.5 GA-Final | D12.1 | Not started |  | Get the requirement list before end of Q2
|  |  | TOTAL |  | 5185 | 6481.25
Blue = input (Tier, Net PD, Start Q, End Q, Squad, Status, Owner). Loaded PD, Quarters, PD/quarter and Release are formulas.
Note on F1: Net person-days including tests and docs (the nine DoD conditions). The 25% overhead is applied in Loaded PD.
Note on H1: Quarter the item starts (1-12). Effort spreads evenly across Start Q..End Q on the Quarter Plan sheet.

## Quarter Plan
Quarter plan - capacity versus planned load
Each item's effort is spread evenly across its Start Q..End Q span. Utilisation above 100% means the quarter is overcommitted.
Q | Label | Months | Ramp | Capacity PD | Planned net PD | Planned loaded PD | Utilisation | Milestone / gate
1 | Q1 | M1-M3 | 0.5 | 332.5 | 200 | 250 | 75.19% | G1 - first vertical slice on real hardware
2 | Q2 | M4-M6 | 1 | 665 | 460 | 575 | 86.47% | G2 = R0.1 Alpha
3 | Q3 | M7-M9 | 1 | 665 | 504.5 | 630.625 | 94.83% | G3 - IPsec interop with strongSwan/FortiGate/Cisco
4 | Q4 | M10-M12 | 1 | 665 | 510.2778 | 637.8472 | 95.92% | G4 = R0.5 Beta (MVP), first customer PoC
5 | Q5 | M13-M15 | 1 | 665 | 527.7778 | 659.7222 | 99.21% | BGP + OSPFv2 + BFD + full ACL
6 | Q6 | M16-M18 | 1 | 665 | 475.2778 | 594.0972 | 89.34% | G5 = R1.0 GA-1
7 | Q7 | M19-M21 | 1 | 665 | 522.7778 | 653.4722 | 98.27% | CGNAT, QoS, PKI, WireGuard, IS-IS
8 | Q8 | M22-M24 | 1 | 665 | 540.2778 | 675.3472 | 101.6% | HA state sync, RESTCONF, IPFIX, AAA
9 | Q9 | M25-M27 | 1 | 665 | 422.7778 | 528.4722 | 79.47% | G6 = R1.5 GA-2 (full TNSR parity), MPLS/multicast start
10 | Q10 | M28-M30 | 1 | 665 | 525.7778 | 657.2222 | 98.83% | G7 = R2.0 GA-3 (complete VPP surface)
11 | Q11 | M31-M33 | 1 | 665 | 347.7778 | 434.7222 | 65.37% | Hardening, licensing, documentation
12 | Q12 | M34-M36 | 1 | 665 | 147.7778 | 184.7222 | 27.78% | G8 = R2.5 GA-Final
|  | TOTAL |  | 7647.5 | 5185 | 6481.25 | 84.75%
FINDING: balancing the 102 items against quarterly capacity pushes eight Tier-2 items past Q8 - remote-access VPN, AAA, Terraform/Ansible/SDK, native IKEv2, RPF/ADL, syslog and log explorer, support bundle, and the virtualisation images.
Full TNSR parity therefore completes at the end of Q9 = month 27, not month 24. Three options: (a) accept month 27; (b) add 2 FTE in Q7-Q8 (about USD 120k) and hold month 24; (c) cut those eight items from GA-2 into R2.0. Decide deliberately now rather than discovering it in month 23.
The gap between total capacity and planned load is the programme's contingency reserve. Do not spend it on new scope before month 30.

## Summary
Roll-ups
Every figure is a SUMIF over the WBS sheet. Nothing here is hardcoded.
Domain | Domain name | Net PD | Loaded PD | Share of net
D0 | Foundation & Platform | 685 | 856.25 | 13.21%
D1 | Interfaces & L2 | 300 | 375 | 5.786%
D2 | L3, MPLS & Multicast | 375 | 468.75 | 7.232%
D3 | Dynamic Routing | 540 | 675 | 10.41%
D4 | NAT & CGNAT | 365 | 456.25 | 7.04%
D5 | Firewall & ACL | 270 | 337.5 | 5.207%
D6 | VPN & Tunnels | 650 | 812.5 | 12.54%
D7 | Services, QoS & Host Stack | 575 | 718.75 | 11.09%
D8 | Observability & Ops | 425 | 531.25 | 8.197%
D9 | High Availability | 210 | 262.5 | 4.05%
D10 | Multi-tenancy & AAA | 125 | 156.25 | 2.411%
D11 | Cloud & Virtualization | 130 | 162.5 | 2.507%
D12 | Hardening, QA, Docs & Release | 535 | 668.75 | 10.32%
| TOTAL | 5185 | 6481.25
Tier | Meaning | Net PD | Loaded PD | Share | Duration at plan FTE (months)
T1 | Needed to sell | 3345 | 4181.25 | 64.51% | 18.8628
T2 | Needed for TNSR parity | 1427 | 1783.75 | 27.52% | 8.047
T3 | Complete VPP coverage, low value | 413 | 516.25 | 7.965% | 2.3289
| TOTAL | 5185 | 6481.25
Squad | Squad name | Net PD | Loaded PD | Share of net
S1 | Dataplane & Agent | 860 | 1075 | 16.59%
S2 | Routing & L3 | 840 | 1050 | 16.2%
S3 | Security & VPN | 1200 | 1500 | 23.14%
S4 | Control Plane | 1065 | 1331.25 | 20.54%
S5 | Frontend | 310 | 387.5 | 5.979%
S6 | Platform & Release | 435 | 543.75 | 8.39%
QA | QA / Lab | 355 | 443.75 | 6.847%
Writer | Technical writer | 120 | 150 | 2.314%
| TOTAL | 5185 | 6481.25
CAUTION: the Squad column names the OWNING squad only. Every item's PD includes the API, UI, test and doc work the nine DoD conditions require, so these totals are not staffing loads - do not size a squad from them.
For real staffing, split each item's PD across squads in a separate effort-allocation model, or add per-squad PD columns to the WBS sheet.

## Releases
Release train and gate acceptance criteria
Net PD per release is derived from each WBS item's End Q. 'Lookup key' drives the Release formula on the WBS sheet - do not reorder or delete these rows.
Release | Target month | Gate | Through Q | Lookup key | Scope added | Measurable acceptance criteria | Net PD
R0.1 Alpha | 6 | G2 | 2 | 0 | Foundation, interfaces/L2, live telemetry | 10 Mpps/core IPv4 @64B; kill -9 vpp rebuilds config <30s; UI counters == vppctl | 540
R0.5 Beta (MVP) | 10 | G4 | 4 | 2 | L3/static/VRF, basic NAT44, IPsec S2S, DHCP/DNS/NTP | Customer PoC passed; 100k NAT sessions; commit/rollback with no outage | 877
R1.0 GA-1 | 16 | G5 | 6 | 4 | BGP/OSPF/BFD, full ACL and NAT, VRRP, SNMP, backup and upgrade | 1M-route BGP converges <90s; BFD failover <300ms; 100k ACL rules <2% pps loss; IPsec >=20 Gbps | 1070
R1.5 GA-2 | 27 | G6 | 8 | 6 | IS-IS/OSPFv3/RIP, CGNAT/MAP, WireGuard, PKI, QoS, IPFIX/sFlow, RESTCONF, HA state sync, AAA | 100% TNSR feature matrix signed off; VRRP failover <1s with sessions preserved; >=100 Gbps on 16 workers | 1165
R2.0 GA-3 | 30 | G7 | 10 | 8 | MPLS/SR-MPLS, multicast/BIER, SRv6, LISP, host stack/QUIC/HTTP3, load balancer, multi-tenancy, cloud | Every VPP 26.06 plugin exposed or recorded in a justified out-of-scope list | 708
R2.5 GA-Final | 36 | G8 | 12 | 10 | Hardening, secure boot, licensing, offline updates, pen test, 72h soak, full docs, certification | Zero crashes/leaks over 72h at line rate; clean pen test; signed offline bundle; complete SBOM | 825
[6 empty] | TOTAL | 5185
G1 (month 3) is an internal gate with no release: unattended bare-metal install under 15 minutes, login, NIC inventory, survives reboot.
G3 (month 9): IPsec tunnel up against strongSwan, FortiGate and Cisco peers; three-router static topology forwards traffic.

## Sprints
Sprint plan - first six months
Dates derive from the project start date and sprint length on the Assumptions sheet. Beyond sprint 12, plan one quarter ahead - sprint detail further out is fiction.
Sprint | Start | End | Deliverable (must be demonstrable) | Gate
S01 | 2026-10-01 | 2026-10-14 | Monorepo + green CI + automated QEMU box: Ubuntu 24.04, VPP 26.06, two virtio interfaces bound to VPP
S02 | 2026-10-15 | 2026-10-28 | vrx-agent connects via govpp, Retrieve() dumps interfaces, one gRPC RPC over a unix socket
S03 | 2026-10-29 | 2026-11-11 | vrx-api: GET /api/v1/state/interfaces; schema package with Zod; codegen chain (OpenAPI + client)
S04 | 2026-11-12 | 2026-11-25 | React interface list with live counters over WebSocket -> FULL VERTICAL SLICE PROVEN
S05 | 2026-11-26 | 2026-12-09 | Reconciler core: Descriptor + dependency graph + diff/plan/apply; candidate/running datastore; first atomic commit on MTU
S06 | 2026-12-10 | 2026-12-23 | .deb build + signed APT repo; install on bare metal | G1
S07 | 2026-12-24 | 2027-01-06 | DPDK driver binding from the UI; NIC inventory; startup.conf generator (hugepages/workers/RSS)
S08 | 2027-01-07 | 2027-01-20 | v4/v6 addressing, MTU, MAC, rx-queue placement; confirmed-commit with auto-revert timer
S09 | 2027-01-21 | 2027-02-03 | 802.1q and QinQ sub-interfaces; pending-change bar + diff viewer in the UI
S10 | 2027-02-04 | 2027-02-17 | Bonding/LACP; bridge domains and L2XC; RBAC + audit + API keys
S11 | 2027-02-18 | 2027-03-03 | GSO/checksum offload/jumbo; loopback/BVI; LLDP; autoinstall ISO
S12 | 2027-03-04 | 2027-03-17 | kill -9 vpp in nightly CI; TRex baseline | G2 = R0.1 Alpha
Sprint 4 is the checkpoint that matters: a full vertical slice (VPP -> Go agent -> gRPC -> Node API -> React with live counters) proves the whole architecture in six weeks. If it slips, re-plan before writing more features.
Formulas:
End = [Start]+7*Assumptions!$B11-1

## Team
Team structure and hiring plan
The capacity math on the Assumptions sheet uses delivery FTE, not raw headcount.
Squad | Name | Headcount | Hire by | Responsibility | Key skills
S1 | Dataplane & Agent | 3 | M1 | VPP plugins, govpp, reconciler, renderers, stats | C, Go, DPDK, VPP internals
S2 | Routing & L3 | 2 | M1 | linux-cp, FRR, BGP/OSPF/IS-IS, MPLS, multicast, FIB | Go, network engineering (CCIE/JNCIE)
S3 | Security & VPN | 2 | M6 | IPsec, strongSwan, PKI, WireGuard, NAT, ACL | Go, cryptography, IKE
S4 | Control Plane | 2 | M1 | NestJS, commit engine, RBAC, telemetry, RESTCONF, SDKs | Node.js, TypeScript
S5 | Frontend | 2 | M1 | React/MUI, SchemaForm, dashboards, i18n/RTL | React, TypeScript, UX
S6 | Platform & Release | 1 | M1 | VPP build, packaging, images, APT, upgrade, CI | DevOps, Debian packaging
QA | QA / Lab | 2 | M3 | Robot Framework, TRex, interop, nightly, perf CI | Network test automation
Arch | Architect / TPM | 1 | M0 | Architecture, review, planning (50% delivery) | -
Writer | Technical writer | 0.5 | M12 | User docs, CLI/API reference | -
| TOTAL HEADCOUNT | 15.5
The binding constraint is one senior VPP/DPDK engineer. Start recruiting before month 0 - that hire, not this plan, decides the schedule.
Hiring order: M0 architect + senior VPP engineer ¦ M1 2xGo, 2xNode, 1xReact, 1xDevOps ¦ M3 1xReact, 1xQA ¦ M6 1xGo, 1x senior network engineer, 1xQA/perf ¦ M12 technical writer.

## CapEx
Lab capital expenditure
A performance claim without a traffic generator is marketing fiction. The month-4 purchase is not optional.
Month | Items | Cost (USD) | Cumulative (USD)
M0 | 2 lab servers (single socket, AES-NI, AVX2) + Intel XXV710 25G NICs + 25G switch | 40000 | 40000
M4 | TRex traffic generator box + Intel E810 100G NICs - no performance claim is defensible without it | 35000 | 75000
M10 | HA pair + second switch + ConnectX-6 for the rdma driver path | 30000 | 105000
M18 | 100G switch + optics + Intel QAT card for crypto offload | 35000 | 140000
M24 | Interop gear: used Cisco/Juniper router, FortiGate unit | 25000 | 165000
| TOTAL | 165000
Order-of-magnitude estimates for used and current-generation COTS hardware as at September 2026. Obtain live quotes before budgeting.

## Scenarios
Scope and staffing scenarios
Delivery months = loaded PD / (FTE x PD-per-year / 12). Total months adds the ramp-up and stabilisation allowance from the Assumptions sheet - calendar time that does not compress by adding people.
Scenario | Scope | Net PD | Loaded PD | Delivery FTE | Delivery months | Total months | Risk assessment
A Aggressive | All (T1+T2+T3) | 5185 | 6481.25 | 22 | 18.6065 | 24 | Critical path does not parallelize; coordination overhead rises about 15%; hiring 22 VPP-capable engineers is unrealistic in most markets.
B Recommended | All (T1+T2+T3) | 5185 | 6481.25 | 14 | 29.2387 | 34 | Balanced. This is the plan in this workbook.
C Lean | All (T1+T2+T3) | 5185 | 6481.25 | 10 | 40.9342 | 46 | Falls behind the VPP release cadence and market timing; the VPP rebase cost recurs every four months.
D Smart | Tier 1 only | 3345 | 4181.25 | 14 | 18.8628 | 24 | LOWEST RISK, BEST RETURN. A sellable product with every critical capability; revenue funds T2 and T3.
E TNSR parity | Tier 1 + Tier 2 | 4772 | 5965 | 14 | 26.9098 | 32 | Balanced; drops only the 8% of scope that no router customer requests.
Scenario A's figure assumes perfect parallelism, which the critical path (reconciler core -> linux-cp -> BGP) forbids. Treat it as a floor, not a plan.
Scenario B computes to 34 months while the plan on the Quarter Plan sheet runs 12 quarters = 36 months. The two extra months are deliberate planning slack; do not remove them to make a date.